## Sheet1
Due Dates | [6 empty] | 2/5 Abstract Due |  | 2/15 Presentation I |  |  |  | 3/18 Interim Report | Presentation II |  |  | 4/15 Final Report Draft/Poster Draft | 4/22 Final Poster |  | 5/1 Final Report/60 Sec Vid
Weeks: | 12/20 | 12/27 | 1/3 | 1/10 | 1/17 | 1/24 | 1/31 | 2/7 | 2/14 | 2/21 | 2/28 | 3/6 | 3/13 | 3/20 | 3/27 | 4/3 | 4/10 | 4/17 | 4/24 | 5/1
Julian | 12/20: Gantt Chart & Proposal Finalization; 12/27: Break
Define Project Framework and Tools
Abstract Preparation
Building Back End (Processing, Storage, Tools)
Presentation I Preparation
Negative Sentence % & Ex
Adj Sentiment Breakdown
[11 empty] | "You are" identity speculation/ Family Member Detection | Refinemint of You Are & Family
[11 empty] | Location & Gender Detection | You like to discuss/You Like
[11 empty] | You like to watch/ like to play | Sentiment over time/By Subreddit
NLP accuracy improvement using grammar check & spelling statistics
Sujay | 12/20: Gantt Chart & Proposal Finalization; 12/27: Break; Presentation II 3/20: Subreddit Equivalents of all features & trending topics within sub
|  |  | Define Project Framework and Tools |  |  |  |  | s | [7 empty] | 4/15 Final Report Draft/Poster Draft
[5 empty] | Abstract Preparation | [11 empty] | 4/22 Final Poster
[5 empty] | Building Back End (Processing, Storage, Tools) | [13 empty] | 5/1 Final Report/60 Sec Vid
Presentation I Preparation
Design user page front end
[9 empty] | Initial NLP code construction | Populate front end
Get user top details/subreddits participated in
Create graph directives
Design subreddit page front end/Get subreddit data and analysis
Matt | 12/20: Gantt Chart & Proposal Finalization; 12/27: Break; 2/15 Presentation I 3/6: Work on interim report and Presentation II
|  |  | Define Project Framework and Tools | [10 empty] | Implement subreddit features in front end
[5 empty] | Abstract Preparation | [8 empty] | Test/Improve existing code, add existing features if time allows
[5 empty] | Building Back End (Processing, Storage, Tools) | [10 empty] | 4/15 Final Report Draft/Poster Draft
[8 empty] | Presentation I, Documentation | [8 empty] | 4/22 Final Poster
[9 empty] | Comment metadata and analysis | [9 empty] | 5/1 Final Report/60 Sec Vid
Get user submissions and get metadata/analysis
Get subreddit data and get metadata/analysis
Work on interim report and Presentation II
Test/Improve existing code, add existing features if time allows
4/15 Final Report Draft/Poster Draft
4/22 Final Poster
5/1 Final Report/60 Sec Vid
Kanav | 12/20: Gantt Chart & Proposal Finalization; 12/27: Break
Define Project Framework and Tools
Abstract Preparation
Building Back End (Processing, Storage, Tools)
Presentation I Preparation
Negative Sentence % & Ex
Adj Sentiment Breakdown
[11 empty] | "You are" identity speculation/ Family Member Detection | Refinemint of You Are & Family
[11 empty] | Location & Gender Detection | You like to discuss/You Like
[11 empty] | You like to watch/ like to play | Sentiment over time/By Subreddit
NLP accuracy improvement using grammar check & spelling statistics
Subreddit Equivalents of all features & trending topics within sub
4/15 Final Report Draft/Poster Draft
4/22 Final Poster
5/1 Final Report/60 Sec Vid